## ww2
Date | Sl No | Task | Status | Review | Comments | Test Execution count | Debug Support
2021-01-04 | 1 | Banglore target bring up (BASVHOST45,BASVHOST80) | complete |  | tried to install agama 193 in both targets BASVHOST45 and BASVHOST80 .in BASVHOST 45 ,it is showing no devices found in the platform.
2021-01-05 | 2 | Agama installation in BA targets | complete |  | OS corrupt observed in both BA targets asked for lab support as the tests are failing with logs (driver not supported)
2021-01-06 | 3 | compute and media test case executions OSBV runs in archer city platform | complete |  | Below is the Mock Execution Status on ArcherCity + ATS-1T combo. Compute:- • 2/4 Compute case got passed. • 2/4 Compute case got failed. Media:- • 7/10 Media test case got Passed. • 2/10 Media test case got Failed. • 1/10 We need input files from Media Team. | 14
2021-01-07 | 4 | re-run of failed cases in archercity -1T platform. | complete |  | atomic_add_index_bin FAILED 1 subtest is failing in compute atomic test ,SGEMM test case is failing.in media two transcode cases are failing even after multiple re-runs | 5
2021-01-08 | 5 | media and compute failed cases | complete |  | 1 case from compute and 1 transcode case in media is passing for another compute test agama latest build is needed , trying to install aagama 180 or any higher versions | 2

## ww3
Date | Sl No | Task | Status | Review | Comments | Test Execution count | Debug Support
2021-01-11 | 1 | BA targets bring up | complete |  | installed agama_203 in both BA targets
2021-01-12 | 2 | BASVHOST80 target check by running compute tests | complete |  | basic compute tests are running planned to run media and media+PM | 4
2021-01-13 | 3 | PM cases execution | complete |  | RC6 enabled ? : sudo vim /etc/modprobe.d/i915.conf dmesg(to get info) ----------------------------------------- ---------------------------------------------------- import toolext.bootscript.boot as b import articsound.debug.domains.gfx.gt.gtPmStatus as pms pms.gtPmHarassers(n_tiles=2) | 2
2021-01-15 | 4 | resolving itp.unlock( ) issue | in progress |  | facing itp.unlock issue() , as it showing unauthorised even for those who has itp.access

## ww4
Date | Sl No | Task | Status | Review | Comments | Test Execution count | Debug Support
2021-01-18 | 1 | PM runs in hyderabad target | complete |  | tried to execute PM cases in hyderabad target as the banglore targets itp.unlock is not working, in hyd target test cases are running but the gt.frequency is hitting 1100, tried to enable RC6 in the target but sudo vim /etc/modprobe.d/i915.conf file is showing empty.
2021-01-19 | 2 | working with BA team to resolve target issues | complete |  | BA targets for media+PM cases , trying possible ways to resolve itp issue , restarting the target, using the credentials from BB's
2021-01-20 | 3 | on leave |  |  | on leave
2021-01-21 | 4 | BA target booting up (CAT errors) | complete |  | BASVHOST80 target is not booting as it showing CAT errors , tried running python scripts to bring up the target, target booted , sucessfully but itp.unlock() for ATS card is showing locked
2021-01-22 | 5 | re-run the bootscript and use sv.refresh() and itp.forcereconfig() and try again. | in progress |  | itp.unlockstatus() ICX0_CLTAP0 is unlocked to Red LBG_CLTAPC0 is locked ATS_CLTAP0 is locked ATS1_CLTAP0 is locked tried to unlock using the script but the status is showing as locked, tried updating python sv ,but unlock is not happening

## ww5
Date | Sl No | Task | Status | Review | Comments | Test Execution count | Debug Support
2021-01-25 | 1 | resolving basvhost80 issues | complete |  | BASVHOST 80 on trying sv.gfxcard0.tile0.uncore.pcode_io.io_core_status_0.show sv.refresh() itp.forcereconfig() import toolext.bootscript.boot as b b.go(pwrgoodmethod='manual') giving cat errror and target not responding.
2021-01-27 | 2 | hyd and BA targets bring up. | complete |  | Tried to install agama 180 driver, as the old one is not properly installed , faced core dumped issues , requested labteam for fresh preload OS.
2021-01-28 | 3 | CTS content overview | underprocess |  | 1. Extract the attached file into a folder 2. Get the Grits Toolchain for PVC (PVC-47728-Linux) and extract them to any folder 3. Launch Fulsim with below command from the directory where the files are extracted a. <Path to PVC-47728-Linux>/AubLoad -device pvc:2tx8x8x8:a0 ccsEnableMask=0x0 rcsEnableMask=0x0 -targetconfig ./PVC_Platform_config_2tile_8GB.xml -enableFeature 1408921788 -enablefeature 1409400390 -enablefeature 1406907150 2203915042 -socket tcp:0 4. In the Fulsim log, check for message similar to “Listening on port: 42069" (Use this number in next step) 5. Create a empty file “targetinfo.txt” and add below line (followed by a blank line) a. 127.0.0.1:42069 6. Run blt_random with required arguments
2021-01-29 | 4 | CTS sample case execution | complete |  | tried to run CTS content on wilson city target, as the listening port required another instance, requested another linux installed system for execution. | 1