## ww6
Date | Sl No | Task | Status | Review | Comments | Test Execution count | Debug Support
2021-02-01 | 1 | compute OCL cases (binaries) execution | complete |  | executed all the SGEMM cases ,workgroups and subgroups basic,workloads related to OCL by copying the test related binaries from GIT.
2021-02-02 | 2 | compute (Binnocle) test case execution | complete |  | moved binnoble-3.3 folder from gar path to ATS machine and run the binocle test by changing the config.txt file using test i.d's all tests got passed except atomic test(WPARID) | 18
2021-02-03 | 3 | compute failed and pending cases | complete |  | • 1/22 Requires input from unit owner (GPGPU Walker Test Python based). • 1/22 Test got failed (Atomic Test (WPARID)) sent the failed case logfile for the compute to review and asked for GPGPU test related binaries.
2021-02-04 | 4 | media cases log files collecting in basvhost80 | complete |  | as hyderabad target is down to collect logs executed the same media cases in basvhost80 and forwarded the log file path in gar path to mrigendra. Path :\\gar\ec\proj\deg\GFXSV\PVC\Execution\media_logfiles
2021-02-05 | 5 | HYD target bringup. | underprocess |  | tried installing agama version:193 in hyd target When we install level-zero/level-zero-dev, there is an error sudo apt install ocl-icd-opencl-dev (Still meet error) sudo apt --fix-broken install （fix the previous apt install error）Again "sudo apt install ocl-icd-opencl-dev" after installing target is not booting, target i.p might be changed
18

## ww7
Date | Sl No | Task | Status | Review | Comments | Test Execution count | Debug Support
2021-02-08 | 1 | (core dump) issues solving in taret | complete |  | facing core dump issues while loading the driver, sudo modprobe i915, so tests are unable to run , due to this issue, followed the procedure for installation for agama and neo GPU driver , from the bkm available here :https://wiki.ith.intel.com/pages/viewpage.action?pageId=1721739658 , after reboot target is going to unresponsive
2021-10-09 | 2 | Agama corruption issues in the target | complete |  | driver installations in target While installing use: ‘sudo dpkg -i *.deb’ If any, dependency errors are encountered, you need to manually install them with, ‘sudo dkpg -I –force-all xxxxx.deb’, where xxxxx stands for the package which failed to install.
2021-02-10 | 3 | PM cases execution | complete |  | executed PM cases in hyderabad target after resolving the itp.unlock issue and collected the logs. | 12
2021-02-11 | 4 | GTA in wilson city 1T | complete |  | bring up GTA in wilson city 1T target by assembling the required peripherals , camera logitech application , tera term etc
2021-02-12 | 5 | compute+PM media owners to get source files | complete |  | all the content is executed , for the newly added content , talked to the owners and got the content.
2021-02-14 | 6 | ALL PVC target power on &captured ip adress and system names | complete |  | as part of site power off ,power on all the PVC systems,and captured the i.p adresses with the serail number of the NUC's so that whom ever facin g the ip change issue will be sorted out.
12

## ww8
Date | Sl No | Task | Status | Review | Comments | Test Execution count | Debug Support
2021-02-15 | 1 | Gathering inputs from the media owners. | complete |  | Sent an update to media owners to provide the inputs for the cases that are newly added in ATS queue. working with baghavan to bring up more GTA targets for VV and Archer city target is yet to be bring up as we are facing the network issue on that board
2021-02-16 | 2 | more GTA targets bring up | underprocess |  | in lab, working with baghavan to bring up more GTA systems for volume validation. Facing network issues while booting to linux GTA
2021-02-17 | 3 | AV1 executions in ATS target with boot recipe | complete |  | Working with akash to Run bootscript to disable AV1 (b.go( fusestr=['gt_gfx_gt_c0_r3.gtip_base_fuse_fuse_gt_av1_dis=1']) and check the status of AV1 test case in ATS platform as I got this task from Vivek Gupta. GTA bring up in Archer city platform, target is successfully registered but while booting it is unresponsive. | 2
2021-02-18 | 4 | Archer city 1T bringup | complete |  | Archer city 1T(AC_ATS_1T) configured to GTA , successfully registered the client in the server (http://10.145.162.23:8080/) ,but after running the tests in OS stage it failed to reboot and went unresponsive.
2021-02-19 | 5 | media custom content execution | complete |  | media concurrency tests and custom content tests executed and report sent. | 8
2021-02-20 | 6 | sync up with BA team from 12 to 6 pm on compute checkouts | complete |  | had syncup with BA compute team for compute based checkouts
10

## ww9
Date | Sl No | Task | Status | Review | Comments | Test Execution count | Debug Support
2021-02-22 | 1 | compute binnocle checkouts | complete |  | Sync up with BA team while they are executing compute(160) cases(Binnocle,dldt)in folsom systems, gathering configuration files ,BKM’s, and got one configuration file to run on ATS platform , where 1 cases is failed and remaining are passed. 2) Completed OSBV mock executions on ATS platform. | 10
2021-02-23 | 2 | compute dldt executions from the BKM that got from BA | complete |  | Compute OSBV mock execution(dldt,clpeak) cases,moving the source files to target. 2) Sync up with media team for media cases execution.
2021-02-24 | 3 | preparation of BKM for all the compute related test | complete |  | created BKM for almost all the compute cases (binnocle,stream traid,clpeak,dldt,OCL cases)with all the screenshots while executing a sample test case with changing the configuration files and shared it with the team. And executed sample TAP workloads.
2021-02-25 | 4 | L3 concurrency execution as my name added for L3 by vasuki | complete |  | L3 test runs by sync up with BA team on FM06WVAW0209 system (07.00 PM). &enablement of GTA in Wilson city 2T.
2021-02-26 | 5 | compute checkouts in folsom system | complete |  | compute tapWL's executions in folsom system
10