## ww10
Date | Sl No | Task | Status | Review | Comments | Test Execution count | Debug Support
2021-03-01 | 1 | MCA spin errors resolving in hyd target | complete |  | OSBV binnocle cases execution. >while running the cases with the working configurations , seeing the MCA spin errors ,tried upgrading the kernel ,flashed the working BIOS to resolve the error ,but it is not resolved.
2021-03-02 | 2 | compute (Binnocle) test case execution and raising HSD | complete |  | compute based checkouts in hyd2011 but getting msaspin errors ,updated to the team and asked to raise sightings
2021-03-03 | 3 | OSBV binnocle tests execution | complete |  | planned hyd2016 target for compute based checkouts but PVC card not detecting in the target got info that it a PCI slot issue, moving that setup to archer city and PM checkoutss in BAsvhost targets 106and 108 | 10
2021-03-04 | 4 | copy engine cases executions | complete |  | >>51 copyengine cases are passing in BASVHOST93 >>3 compute are passing . >>debugging the failed cases with different configurations.
2021-03-05 | 5 | BKM creations for executing the cases | complete |  | >>BKM creation for Pm blitter multiengine test cases ,following up for target to execute compute cases which are in bucket0
10

## ww11
Date | Sl No | Task | Status | Review | Comments | Test Execution count | Debug Support
2021-03-08 | 1 | compute bucket 0 cases executions | complete |  | out of 60 pending cases 15 are passing , 35 are failing ,need to check on failures. | 15
2021-03-09 | 2 | compute bucket2 cases execution | complete |  | >>executed combination compute cases from bucket2 in hyd2011 target , we are facing kernel panic issues while execution. >>out of 40 pending cases from bucket0, 12 are passing and 28 are failing
2021-03-10 | 3 | memory copy operations test cases ,bucket2 dldt combination 15 and 16 cases | complete |  | combination 15 and 16 cases most of the cases areshowning error as clGetkernelinfo,errorcode:-48. and only 3 tests got passed. | 3
2021-03-11 | 4 | compute combination 13 & 14 executions. | complete |  | >while running combination 13 and 16, system hang is observed ,collected GT status ,SOC logs and dmesg logs and reported to the team. >>combination2 compute cases are passing and logs are collected. >>prepared BKM for compute with snapshots and mailed.
2021-03-12 | 5 | Atomic access violation errors | complete |  | >>executed BGEMM cases out of 5 cases 3 are passing . >>for other combination GEMM workloads we are facing atomic acess voilation errors,collected the logs and waiting for the reply from domains owners | 3
21

## ww12
Date | Sl No | Task | Status | Review | Comments | Test Execution count | Debug Support
2021-03-15 | 1 | Sample executions from volume validation | complete |  | sample Binnocle cases execution from 5000 test cases ,60 are passing . hyd2011 bring up for 2T binnocle executions | 20
2021-03-16 | 2 | compute failed cases re-run from bucket1 and bucket2 | complete |  | re run compute cases,from bucket1 and bucket2. >>bring up 2011 target for binnocle 2T test cases execution from bucket1 and bucket2. >>bring up gta on 2011 ,for binnocle 2T executions in GTA
2021-03-17 | 3 | sanity check with PLL script | complete |  | sanity check with PLL mode script. some of the cases we observed kernel panic and GT hang
2021-03-18 | 4 | sanity check with PLL mode2 | complete |  | >>GEMM workloads execution on hyd2016 target, as each test taking more than 3 hours , requested for dedicated PC. >>sanity check wit fixed frequency method2 (cases that are failing need to run with the normal PLL script)
2021-03-19 | 5 | fixed frequency executions with po@900, p1,pn @200mhz | complete |  | >>execution of cases with fixed frequency p0-900,p1,pn as 200 ,all cases are passing and for 3 cases observed x11 server issue | 20
40

## ww13
Date | Sl No | Task | Status | Review | Comments | Test Execution count | Debug Support
2021-03-22 | 1 | GEMM executions with fixed frequency. | complete |  | executed GEMM workloads with fixed frequency @900mhz , most of the cases are failing,collected the logs and reported to the team | 0
2021-03-23 | 2 | SGEMM,BGEMM,DGEMM execution | complete |  | executed GEMM workloads with DLL script . executed 17 cases 12 are passing and 3 are errors and 2 are failures. | 12
2021-03-24 | 3 | follow up with domain owner regarding GEMM failures | complete |  | follow up regarding GEMM workloads failures, got updated that they have making some changes to kernel to work with all repeat counts ,they might be pushing the fix today.
2021-03-25 | 4 | IGEMM workloads | complete |  | executed IGEMM workloads 10 are passing , --RX --RY values are by default taking as 1 ,even after supplying with different values, forwarded logs to the compute team , waiting for inputs | 10
2021-03-26 | 5 | IGEMM 10K case execution | complete |  | executed IGEMM 10K case which took 9 hours to execute , collected the logs and updated the queue | 1
23

## ww14
Date | Sl No | Task | Status | Review | Comments | Test Execution count | Debug Support
2021-03-29 | 1 | GEMM Basetest+combination executions | complete |  | executed gemm workloads with combinations(1,2,49) IGEMM,BGEMM | 7
2021-03-30 | 2 | GEMM tests+combinations executions | complete |  | executed gemm workloads with combination(10,12,14,15,1) facing driver issue working on that @hyd2016
2021-03-31 | 3 | GEMM workloads (base tests +random) | in progress |  | executing base test+random combination from 1-10 or 11-20
7
total:101